## Milestones
Milestone | Owner | Baseline Date | Current Forecast | Status | Dependency | Note
Sandbox ready for named users | Elena Markovic | 2026-04-08 | 2026-04-18 | At Risk | Vendor hardening | Recovery path later accepted in Wave 03
Full sandbox capability | Elena Markovic | 2026-04-10 | 2026-04-25 | At Risk | Contract / infra path | Not committed in writing at baseline
FHIR mapping package complete | Jaden Cole | 2026-04-17 | 2026-04-24 | In Progress | Endpoint decisions | Depends on final two endpoint groups
Security summary delivered | Bromley Security Team | 2026-04-15 | 2026-04-18 | In Progress | Endpoint inventory | v1 will ship first
Stakeholder demo rehearsal | Jaden Cole | 2026-04-22 | 2026-04-27 | Watch | Environment validation | Can use mock services if needed

## Change Log
Changed On | Changed By | Item | Old Value | New Value | Reason
2026-03-31 | Lowry Beckett | Sandbox ready for named users | 2026-04-08 | TBD verbal only | Vendor would not commit in writing
2026-04-08 | Elena Markovic | Sandbox ready for named users | TBD verbal only | Approx. two-week slip | Hardening and credential process delay
2026-04-15 | Elena Markovic | Sandbox ready for named users | Approx. two-week slip | 2026-04-18 phased access | Recovery path approved
2026-04-15 | Elena Markovic | Full sandbox capability | TBD verbal only | 2026-04-25 | Broader capability target confirmed